## Sheet1
Req ID | IRC CODE | Issue Summary | Action
SC01, SC02, SC03, SC04 | SUB REA | These level 0 reqrs were phrased as “The system shall allow…”. This does not match the expected Level 0 biz/tech reqrs and reduces clarity and traceability to Level 1. | Revise
SC01.1, SC01.2, SC01.3, SC01.4, SC01.5, SC02.1, SC02.2, SC02.3, SC04.1, SC04.2, SC04.3 | IMP-1 FEA | Weak imperatives. The use of “allow" can be interpreted as a permission rather than a required system behavior. Standard imperatives (Shall, Must) are missing. | Revise
SC03.1, SC03.2 | AMB CMP IMP SUB | 1. “Discover jobs/candidates” and “automated recommendations” do not define relevance factors, ranking inputs, precedence, or behavior when profiles are incomplete. Difficult to model and verify. 2. These are core parts of the job portal system but are marked desirable. Needs confirmation of business priority. | Clarify + Split
RE01, RE02, RE03, RE04, RE05, RE06, RE07 | SUB VER REA AMB | 1. Some reqrs are too low-level to be Level 0 reqrs. 2. Reqrs stated are not verifiable; “secure hashing”, “apply retention policy”, “enforce type restrictions", “enforce validation constraints”, “authorisation conditions defined by policy” 3. Some reqrs are ambiguous and unclear | Revise + Clarify
RE04 | VER CMP AMB | The constraints “According to PDPA retention guidelines” are vague, as there are no retention periods, data categories, and deletion/anonymisation rules. Not verifiable as written. | Clarify + Revise
RE07 | IMP-1 | “The system assumes…” is missing the standard imperatives. | Revise
AR04.1 (API spec), AR04.1 (auth service) | CS REA | Duplicate reqr code AR04.1 is used for two different reqrs. This breaks traceability, repository indexing and modelling references. | Revise
AR02.1a, AR02.2a, AR04.1 (API spec), AR02.2 | SUB | Reqrs focused on implementation; too low level. API spec out of scope of tech reqrs. | Remove
RE03.1, RE03.2 | SUB | Reqrs too techie and implementation heavy. | Revise
SC01.3a | AMB ATM | Reqr ambiguous; “secure file storage”, “associate stored files with job seeker profiles”. Atomic as it includes both biz and tech reqrs. | Clarify+ Revise