## Sheet1
Meeting ID | Date | Time | Location | Attendees | Agenda | Topic/Requirement ID | Key Decisions/Resolutions | Action Item
Meeting ID | Date | Time | Location | Attendees | Agenda | Topic/Requirement ID | Key Decisions/Resolutions | Action Item
MTG-CLAR-01 | 2026-02-05 | 10:00 | Uwais Agency HQ | NexaSpring: Cheng Yi Zhen (Requirements Analysis Lead), Derick Lee (BA Lead), Sarah Tan (Account Manager) Uwais Hiring Agency: Stuart Lim (PM), Amanda Raj (Head of Recruitment) | Resolve ambiguity in matching algorithm logic | Automated Recommendations (SC03) | Visual: System-Context- Diagram Logic Defined: 1. Skills Match (High) 2. Years of Exp (Med) 3. Location (Low). Incomplete profiles excluded. | Rewrite SC03 as a functional requirement.
MTG-CLAR-02 | 2026-02-05 | 10:30 | Uwais Agency HQ | NexaSpring: Cheng Yi Zhen (Requirements Analysis Lead), Derick Lee (BA Lead), Sarah Tan (Account Manager) Uwais Hiring Agency: Stuart Lim (PM), David Chen (DPO) | Clarify data retention policy and post-retention behavior | PDPA & Retention (RE04) | Visual: System-Context- Diagram, User-Data-Lifecycle Rule Defined: After 24 months of inactivity, strip NRIC/Name (Anonymize). Do NOT hard delete. | Update RE04 to specify "24-month anonymization".
MTG-CLAR-03 | 2026-02-05 | 11:15 | Uwais Agency HQ | NexaSpring: Cheng Yi Zhen (Requirements Analysis Lead), Derick Lee (BA Lead), Sarah Tan (Account Manager) Uwais Hiring Agency: Stuart Lim (PM), Farhan Malik (Lead Architect) | Relocate low-level implementation details | Technical Constraints (RE01-06) | Visual: NIL Decision: Combine low level requirements and create more broad high level requirement for RE reqrs | Combined RE reqrs to create new high level requirmeents
MTG-CLAR-04 | 2026-02-07 | 14:00 | MS Teams Call | NexaSpring: Derick Lee (BA Lead) Uwais Hiring Agency: Stuart Lim (PM) | Walkthrough of the drafted text for the Interpret phase handoff | Review of Revised Reqs | Decision: Client approved the rewritten statements for matching logic and PDPA. | Proceed to Categorize phase and map to IEEE 830.